## SPM_release_plan
Release number |  |  |  |  | 1
Wished Date |  |  |  |  | 2023-10-15
Start Date |  |  |  |  | 2023-10-06
Amounts of days |  |  |  |  | 25
Candidate Day |  |  |  |  | 2023-11-19
Feature in release | Category | Priority | Status | Description | Blocks, Comments and Dependecies
Transmission of CAN Wake-up frames | lSPM-to-rSPM communication (Tx) |  | Accepted | Build the payload of a CAN Wake-up frame in the SPM and transmit it using the lower layers of the AUTOSAR stack. SPM-CAN: MCAL level | definition of Ethernet wake-up still missing. Skip for this release
Transmission of Heartbeat Frame | lPM-to-rPM communication (Tx) |  | Accepted | serialize the data in SOME/IP protocol package and send it on the Ethernet bus.
Transmission of SPM target notification messages | lSM-rSM communication (Tx) |  | Accepted | Message at this scope are: 1. Activation and Deactivation request 2. Request Acknowkedge 3. Profile Status information Messages shall be in separated PDU or in a single one. | ACK is produced by the Offerer of the service to the consumer. Why it is in Consumer request message? ASSUMPTION: ACK is in a pipeline. Consumer produces an ACK for a Service for which it is a offerer.
Reception of the CAN Wake-up frames | lSPM-to-rSPM communication (Rx) |  | Accepted | Define an handler for the reception of the CAN wake-up frame from the Can_Drv or Can_If. | Message format and Synchrnoization/scheduling can be the critical points The masking/filtering mechanism/algorithm can be also in scope to this development
Reception of the SPM target notification messages | lSM-rSM communication (Rx) |  | Accepted | Define an handler to trogger the reception and a stub to unpack the messages. | Use of RTE/SomeIp_Xfrm plus the LdCom. Standard autosar stcak can be use Try to think about the critical path with the longest possible messages Explore the specification on these topoics
Parsing the power profile | Power Profile Management |  | Accepted | 1. Obtain the information from a local DB 2. Define the ParamDef for the Power Profile | Configuration dependet work. GM asks for the Conf-gen on this topic. Alignment with the FAE team might be necessary

## SPM_development_plan
Release number |  |  |  | 1
Task | Priority | Jira Ticket | Description | Day (8hr) estimation | Start Date | End date | Activity | Development
Proposal for port-interface fro SPM mesages through the Com, LdCom | 0 |  | Ports will be used to come out-from the SPM to the transformer | 5 |  |  | Accepted | In-Progress
Proposal for SPM paramdef | 0 |  | Define all the parts for the Power Profile configuration | 0 |  |  | Accepted | Done
Proposal for the data structure that are generated by the configuration of power profile and messages | 0 |  | Define the structure in teh code to contain the data | 0 |  |  | Accepted | Done
Analyze interaction between SPM and Can_Drv and/or Can_If | 1 |  | Look the specification to understand how to send a messge on can by-passing the higher levels in AUTOSAR. Understand if use the Can_If or Can_Drv. | 2 |  |  | Accepted | In-Progress
Analyze interaction between SPM and LdCom | 1 |  | Understasnd how to put in communication the SomeIp_Xfrm with the LdCom and if the LdCom can direc speaks with the SPM | 2 |  |  | Accepted | In-Progress
Analyze interaction between SPM and SomeIp_Xfrm (RTA-RIPs?) | 1 |  | Which API shall be called once that the Payload data are ready? | 2 |  |  | Accepted | In-Progress
UG and RN | 1 |  | Define the main components/modules within the SPM. The divisio should be done by functional/logic point of view | 3 |  |  | Accepted | To-do
Define function for receiving data directly to CAN lower Layer | 1 |  | SPM CDD speaks with the driver/interface to receive the can wake-up frame and implements the filtering | 5 |  |  | Accepted | In-Progress
Define data structure to contain the field of data message | 2 |  | Define the structures as per SDV-2017 | 0 |  |  | Accepted | Done
Define integration function to contain the activation logic for a local activation request | 2 |  | Define a function prototype in order to get the logic of the activation of the power profile | 1 |  |  | Accepted | In-Progress
Define function for transmitting data directly to CAN lower Layer | 2 |  | SPM CDD speaks with the driver/interface to send the CAN wake-up frame. This requires the definition of the payload | 2 |  |  | Accepted | In-Progress
Define function (stub) to create the payload for SPM messages | 2 |  | This is the main function to build the main payloads for the messages | 0 |  |  | Accepted | Done
Interaction between SPM and SecOc for the receiving path | 2 |  | The receiving SPM messages are in Secure I-PDU, therefore in the receiving path, the SPM shall manage the returning from the SecOc to verify the PDU | 0 |  |  | Accepted | To-do
Define an Sum_SPM_EnableModule flag to start the module (manually trigger) | 4 |  | Probaly an IRV for enabling the execution of the module functions | 0 |  |  | Accepted | To-do
Define an Sum_Spm_Init() and a Spm_Main() | 4 |  | This just for initializing module states and variables | 2 |  |  | Accepted | In-Progress
Define Configuration and Calibration Parameter for messages and messages fields | 4 |  | Some messages as the Heartbeat needs a timer with a configuration value for the initial one and then, it can be calibrable | 1 |  |  | Accepted | In-Progress
Define the ParamDef for the Power Profile | 4 |  | Define the parameter definition and structure fo the containers to store the information as GM describes the database | 0 |  |  | Accepted | Done
Total Days: |  |  |  | 25